## Summary
Replication package check: 1-original-package
Checked 2026-10-07 with check_package.py 1.0. Automated first pass: review every finding.
Severity | Findings | Still open | What it means
High | 11 | 11 | Likely to stop the code running, or to fail the journal's code check
Medium | 18 | 18 | The data editor will probably ask for a change
Low | 5 | 5 | Good practice, quick to fix
Info | 0 | 0 | For your information
Total | 34 | 34
How to use this workbook
On the Findings sheet, edit only the yellow columns: Status (pick from the list) and Notes.
The counts above update by themselves. 'Still open' counts findings whose Status is Open.
Status values: Open, Fixed, Author to decide, Not an issue.
For CSV files only the header row was read. No data values were opened or copied here.

## Findings
ID | Severity | Check | Where | Finding | Suggested fix | Status | Notes
F01 | High | README | README.txt | Section missing: Data availability and provenance statements. | Add a data availability statement: where each dataset comes from, whether it is included, and how a replicator can get any data that is not included (cost, wait time, application). | Open
F02 | High | README | README.txt | Section missing: Computational requirements. | Add the software and versions used (including packages), the operating system, and hardware. | Open
F03 | High | README | README.txt | Section missing: Instructions to replicators. | Add step-by-step instructions: what to install, which single script to run, and where the results appear. | Open
F04 | High | README | README.txt | Section missing: List of tables and figures with the programs that make them. | Add a table mapping every table and figure in the paper to the program (and line) that creates it and the output file name. | Open
F05 | High | Master script | (package) | No master script found. Nothing runs the whole package from start to finish. | Add one master script in the top folder (main.py, main.R or main.do from templates/) that runs every program in order and writes a log. | Open
F06 | High | Paths | code/analysis.py (line 7) | Hard-coded absolute path: `/Users/jroe/Dropbox/tutoring-paper/`. It points into a synced folder (Dropbox, OneDrive or similar). | Build paths from the package folder: ROOT = Path(__file__).resolve().parents[1], then ROOT / "data" / "raw" / "file.csv". | Open
F07 | High | Paths | code/clean_data.py (line 6) | Changes the working folder to a hard-coded path: `C:/Users/jdoe/Dropbox/tutoring-paper`. It points into a synced folder (Dropbox, OneDrive or similar). | Build paths from the package folder: ROOT = Path(__file__).resolve().parents[1], then ROOT / "data" / "raw" / "file.csv". | Open
F08 | High | Paths | code/clean_data.py (line 8) | Hard-coded absolute path: `C:/Users/jdoe/Dropbox/tutoring-paper/data/raw/tutoring_pilot.csv`. It points into a synced folder (Dropbox, OneDrive or similar). | Build paths from the package folder: ROOT = Path(__file__).resolve().parents[1], then ROOT / "data" / "raw" / "file.csv". | Open
F09 | High | Paths | old/robustness_check.do (line 2) | Changes the working folder to a hard-coded path: `C:\Users\jdoe\Dropbox\tutoring-paper`. It points into a synced folder (Dropbox, OneDrive or similar). | Set the root once in the master do-file (global root "`c(pwd)'") and write paths as "$root/data/raw/file.dta". | Open
F10 | High | Data files | old/robustness_check.do (line 3) | Reads `robustness_sample.dta`, which is not in the package. | Add the file. If the data are restricted or confidential, keep the code, and explain in the README's data availability section how a replicator can get access. | Open
F11 | High | Personal data | data/raw/tutoring_pilot.csv | Column names suggest personal data (name: student_name; email: parent_email; phone: phone; address: home_address; birth date: dob). Only the header row was read; no values were opened. | Ask the author. If these are real identifiers, remove the columns before publishing (if the analysis does not use them) or move the file to restricted access and explain access in the README. Do not open or share the values. | Open
F12 | Medium | README | README.txt | Section missing: Statement about rights (permission to use and share the data). | State that the authors may use the data and may (or may not) share them, and under which licence or terms. | Open
F13 | Medium | README | README.txt | Section missing: Dataset list (each data file, its source, and whether it is provided). | Add a table of every data file: name, source, whether it is provided, and its format. | Open
F14 | Medium | README | README.txt | Section missing: Hardware and run time. | Say how long a full run takes and on what computer (processor, memory, operating system). | Open
F15 | Medium | README | README.txt | Section missing: Description of programs. | Describe the programs: what each folder and script does, in the order they run. | Open
F16 | Medium | README | README.txt | Section missing: References and data citations. | Add a References section that cites every dataset (creator, year, title, publisher or repository, version, DOI or web address). | Open
F17 | Medium | README | README.txt | The README does not say which version of Stata was used. | Add the exact version (for example Stata/MP 18.0) under Computational requirements, and check it with the author. | Open
F18 | Medium | README | README.txt | The README does not say which version of Python was used. | Add the exact version (for example Python 3.11.9) under Computational requirements, and check it with the author. | Open
F19 | Medium | README | README.txt | No data citation found (no DOI or web address in the README). | Cite each dataset in the References section with a DOI or a stable web address, and cite the same datasets in the paper. | Open
F20 | Medium | Paths | code/figure1.py (line 6) | Path inside one person's home folder: `~/Dropbox/tutoring-paper/data/derived/analysis_sample.csv`. It works only on that computer. It points into a synced folder (Dropbox, OneDrive or similar). | Build paths from the package folder: ROOT = Path(__file__).resolve().parents[1], then ROOT / "data" / "raw" / "file.csv". | Open
F21 | Medium | Paths | code/figure1.py (line 40) | Path inside one person's home folder: `~/Dropbox/tutoring-paper/output/figure1_scores_by_baseline.png`. It works only on that computer. It points into a synced folder (Dropbox, OneDrive or similar). | Build paths from the package folder: ROOT = Path(__file__).resolve().parents[1], then ROOT / "data" / "raw" / "file.csv". | Open
F22 | Medium | Paths | old/robustness_check.do (line 3) | Path written with backslashes: `data\derived\robustness_sample.dta`. This works only on Windows. | Use forward slashes (data/raw/file.csv). They work on Windows, Mac and Linux. | Open
F23 | Medium | Paths | old/robustness_check.do (line 11) | Path written with backslashes: `output\tableA2_robustness.tex`. This works only on Windows. | Use forward slashes (data/raw/file.csv). They work on Windows, Mac and Linux. | Open
F24 | Medium | Dependencies | old/robustness_check.do | Uses Stata community commands with no list or copy of them: eststo, esttab, reghdfe. | Save the exact ado files inside the package (an ado/ folder set up in the master do-file, see templates/main.do) and list them with versions in the README. | Open
F25 | Medium | Dependencies | requirements.txt | Packages listed without exact versions: matplotlib, pandas, statsmodels. | Pin each one with ==, using the versions the author actually used (pip freeze on their computer), not today's latest versions. | Open
F26 | Medium | Dependencies | requirements.txt | Imported in the code but not in the package list: numpy (imported in code/analysis.py); scipy (imported in code/analysis.py). | Add each one with its exact version (name==version). | Open
F27 | Medium | Outputs | output/tableA1_attrition.csv | No program in the package appears to create this file. | Ask the author for the program that makes it and add it to the master script and the table/figure list. If the file is not in the paper, remove it. Never recreate an output by hand. | Open
F28 | Medium | Randomness | old/robustness_check.do (line 8) | Uses random numbers but no seed is set: `bootstrap _b, reps(500) cluster(school_id): regress endli...`. | Set a seed once, e.g. set seed 20240101, and describe it in the README. A new seed can change results slightly: agree with the author first and report any change. | Open
F29 | Medium | Logs | (package) | No log files, and no code that writes a log. | Have the master script save a log of the full run (templates/main.* do this), run it once, and include the logs in the package. | Open
F30 | Low | README | README.txt | Section missing: Overview. | Add a short overview: what the package reproduces, which script to run, and roughly how long it takes. | Open
F31 | Low | Paths | code/clean_data.py (line 2) | Absolute path in a comment: `D:\projects\tutoring\raw`. | Harmless when running, but it reveals where files lived on the author's computer. Delete or update the comment. | Open
F32 | Low | Dependencies | (Stata code) | No version statement in the do-files. | Add version NN (the Stata version the author used) near the top of the master do-file. | Open
F33 | Low | Housekeeping | (package) | No LICENSE file. | Ask the author which licence to use for code and data (for example MIT for code, CC BY 4.0 for data they own) and add a LICENSE file. | Open
F34 | Low | Housekeeping | output/Thumbs.db | 1 stray system or temporary file(s) or folder(s). | Delete them from the deposit (they are created by Mac, Windows, Python, R or Office). | Open

## Files
Path | Size (MB) | Type | Role
code/analysis.py | 0.003 | .py | Code (Python)
code/clean_data.py | 0.001 | .py | Code (Python)
code/figure1.py | 0.002 | .py | Code (Python)
data/raw/tutoring_pilot.csv | 0.076 | .csv | Data
old/robustness_check.do | 0 | .do | Code (Stata)
output/figure1_scores_by_baseline.png | 0.088 | .png | Output
output/table1_summary_stats.csv | 0 | .csv | Output
output/table2_main_results.csv | 0 | .csv | Output
output/tableA1_attrition.csv | 0 | .csv | Output
README.txt | 0 | .txt | Data
requirements.txt | 0 | .txt | Data