## Submittal Log
SUBMITTAL LOG
Project | Harborview Family Clinic - Tenant Fit-Out (fictional project) |  |  |  |  | Project no. | 2026-014
Subcontractor | Northgate Mechanical Services (fictional) |  |  |  |  | General contractor | Quellmoor Builders (fictional)
Prepared by | Sample Document Services |  |  |  |  | Log updated | 2026-10-07
Yellow cells are for you to fill in. Days in review and Late? are worked out for you. This log tracks paperwork only; it does not confirm that anything complies.
Submittal No. | Rev | Spec section | Description | Type | Submitted to | Date required | Date submitted | Date returned | Status | Days in review | Late? | Ball in court | Next action | Reviewer comments / notes | File name
23 05 93-001 | 0 | 23 05 93 | Test and balance agency qualifications | Certificates | Quellmoor Builders (fictional) | 2026-03-02 | 2026-02-20 | 2026-02-27 | Approved | 7 |  | Subcontractor | Filed |  | 23 05 93-001_R0_TAB-Qualifications.pdf
23 74 00-001 | 0 | 23 74 00 | Packaged rooftop unit RTU-1 - product data | Product data | Quellmoor Builders (fictional) | 2026-03-09 | 2026-03-03 | 2026-03-13 | Approved as noted | 10 |  | Subcontractor | Order unit with the noted option | Provide factory-mounted disconnect. | 23 74 00-001_R0_RTU-1_Product-Data.pdf
23 34 23-001 | 0 | 23 34 23 | Exhaust fans EF-1 to EF-3 - product data | Product data | Quellmoor Builders (fictional) | 2026-03-09 | 2026-03-04 | 2026-03-16 | Approved | 12 |  | Subcontractor | Filed |  | 23 34 23-001_R0_Exhaust-Fans_Product-Data.pdf
23 36 00-001 | 0 | 23 36 00 | VAV terminal units - product data | Product data | Quellmoor Builders (fictional) | 2026-03-16 | 2026-03-11 | 2026-03-25 | Revise and resubmit | 14 |  | Subcontractor | Resubmitted as Rev 1 | Reheat coil data missing for VAV-3 and VAV-4. | 23 36 00-001_R0_VAV_Product-Data.pdf
23 36 00-001 | 1 | 23 36 00 | VAV terminal units - product data (resubmittal) | Product data | Quellmoor Builders (fictional) | 2026-04-06 | 2026-04-02 | 2026-04-10 | Approved | 8 |  | Subcontractor | Filed |  | 23 36 00-001_R1_VAV_Product-Data.pdf
23 09 00-001 | 0 | 23 09 00 | HVAC controls - product data and sequence of operations | Product data | Quellmoor Builders (fictional) | 2026-04-13 | 2026-04-08 | 2026-04-24 | Approved as noted | 16 |  | Subcontractor | Update sequence as noted | Add night setback to the sequence. | 23 09 00-001_R0_Controls.pdf
23 07 00-001 | 0 | 23 07 00 | HVAC insulation - product data | Product data | Quellmoor Builders (fictional) | 2026-04-20 |  |  | Not submitted |  | LATE | Subcontractor | Chase supplier for datasheets
01 78 23-001 | 0 | 01 78 23 | Operation and maintenance data - Division 23 HVAC | O&M manual | Quellmoor Builders (fictional) | 2026-10-02 | 2026-09-29 |  | Submitted - under review | 8 |  | General contractor | Await review comments | Final test and balance report to follow. | SAMPLE_OM-Manual_Harborview-Clinic_Div-23-HVAC.pdf
01 78 36-001 | 0 | 01 78 36 | Warranties - Division 23 HVAC | Warranty | Quellmoor Builders (fictional) | 2026-10-02 | 2026-09-29 |  | Submitted - under review | 8 |  | General contractor | Await review comments |  | 01 78 36-001_R0_Warranties.pdf
23 05 93-002 | 0 | 23 05 93 | Final test and balance report | Test reports | Quellmoor Builders (fictional) | 2026-10-23 |  |  | Not submitted |  |  | Subcontractor | Waiting for balancing contractor
01 78 39-001 | 0 | 01 78 39 | Record drawings - mechanical | Record drawings | Quellmoor Builders (fictional) | 2026-10-30 |  |  | Not submitted |  |  | Subcontractor | Collect final mark-ups from site
Formulas:
Days in review = IF([Quellmoor Builders (fictional)]="","",IF([Date returned]="",TODAY()-[Quellmoor Builders (fictional)],[Date returned]-[Quellmoor Builders (fictional)]))
Late? = IF(AND(ISNUMBER([General contractor]),[Quellmoor Builders (fictional)]="",TODAY()>[General contractor]),"LATE","")

## Summary
Submittal summary
Harborview Family Clinic - Tenant Fit-Out (fictional project)
Status | Count
Not submitted | 3
Submitted - under review | 2
Approved | 3
Approved as noted | 2
Revise and resubmit | 1
Rejected | 0
For record only | 0
Closed | 0
Total submittals logged | 11
Late to submit | 1
Average days in review (returned) | 11.2

## Lists
Type | Status | Ball in court
Product data | Not submitted | Subcontractor
Shop drawings | Submitted - under review | General contractor
Samples | Approved | Architect / engineer
Calculations | Approved as noted | Owner
Certificates | Revise and resubmit
Test reports | Rejected
O&M manual | For record only
Warranty | Closed
Record drawings
Closeout
Edit these lists to change the drop-down choices.

## Read me
How to use this submittal log
One row per submittal, and a new row for each resubmittal (same number, next Rev). Use the general contractor's numbering if they have one; otherwise spec section + sequence, e.g. 23 34 23-001.
Yellow cells at the top are for the project details. Type and Status have drop-downs (edit them on the Lists sheet). Days in review and Late? are formulas: don't type over them.
Days in review counts from Date submitted to Date returned, or to today while the item is still out. It turns amber after 14 days. Late? shows LATE when the required date has passed and nothing was submitted.
File name: the exact name of the PDF you sent, so you can always find it again.
The Summary sheet counts submittals by status.
Rules
This log tracks paperwork. Approval decisions come from the reviewers. You never certify that a product complies, and you never alter a manufacturer's document.