## Submittal Log
SUBMITTAL LOG
Project | [5 empty] | Project no.
Subcontractor | [5 empty] | General contractor
Prepared by | [5 empty] | Log updated
Yellow cells are for you to fill in. Days in review and Late? are worked out for you. This log tracks paperwork only; it does not confirm that anything complies.
Submittal No. | Rev | Spec section | Description | Type | Submitted to | Date required | Date submitted | Date returned | Status | Days in review | Late? | Ball in court | Next action | Reviewer comments / notes | File name
EXAMPLE 23 34 23-001 | 0 | 23 34 23 | Exhaust fans EF-1 to EF-3 - product data (example row: replace or delete) | Product data | General contractor | 2026-03-02 | 2026-02-24 | 2026-03-06 | Approved as noted | 10 |  | Subcontractor | File the reviewed copy | Confirm motor voltage with the electrical drawings. | 23 34 23-001_R0_Exhaust-Fans_Product-Data.pdf
Formulas:
Days in review = IF([Date submitted]="","",IF([Date returned]="",TODAY()-[Date submitted],[Date returned]-[Date submitted]))
Late? = IF(AND(ISNUMBER([Date required]),[Date submitted]="",TODAY()>[Date required]),"LATE","")

## Summary
Submittal summary
Status | Count
Not submitted | 0
Submitted - under review | 0
Approved | 0
Approved as noted | 1
Revise and resubmit | 0
Rejected | 0
For record only | 0
Closed | 0
Total submittals logged | 1
Late to submit | 0
Average days in review (returned) | 10

## Lists
Type | Status | Ball in court
Product data | Not submitted | Subcontractor
Shop drawings | Submitted - under review | General contractor
Samples | Approved | Architect / engineer
Calculations | Approved as noted | Owner
Certificates | Revise and resubmit
Test reports | Rejected
O&M manual | For record only
Warranty | Closed
Record drawings
Closeout
Edit these lists to change the drop-down choices.

## Read me
How to use this submittal log
One row per submittal, and a new row for each resubmittal (same number, next Rev). Use the general contractor's numbering if they have one; otherwise spec section + sequence, e.g. 23 34 23-001.
Yellow cells at the top are for the project details. Type and Status have drop-downs (edit them on the Lists sheet). Days in review and Late? are formulas: don't type over them.
Days in review counts from Date submitted to Date returned, or to today while the item is still out. It turns amber after 14 days. Late? shows LATE when the required date has passed and nothing was submitted.
File name: the exact name of the PDF you sent, so you can always find it again.
The Summary sheet counts submittals by status.
Rules
This log tracks paperwork. Approval decisions come from the reviewers. You never certify that a product complies, and you never alter a manufacturer's document.